GENERAL CONDITIONS FOR

CONTRACTS UNDER $100,000

TABLE OF CONTENTS:

General Contract Definitions	Page 2-3

General Laws Governing Construction				Page 3

Compliance with and Enforcement of Prevailing Wage Laws	Page 3

Drawings and Specifications 						Page 3 - 4

Construction Bonds							Page 4

Insurance Requirements						Page 4 - 7

General Responsibilities of Owner and Contractor	Page 7

The Contractor’s Responsibility for Jobsite Safety			Page 8

Materials and Workmanship; Licensing and Testing			Page 8 - 9

Shop Drawings and Submittals					Page 9

Contract Payments							Page 9 - 11

Inspection of the Project during Construction			Page 11

Closing Inspections							Page 11

Contract Final Acceptance and Payment				Page 11 - 12

Contract Warranty and Guarantee					Page 12

Concealed Site Conditions 						Page 13

Change Orders 							Page 13 - 14

Time Allotted for Performance; Construction Schedules		Page 14

Modification of the Contract Time					Page 15

Termination and Suspension of the Contract Prior to Comp.	Page 16 - 17

Dispute Resolution							Page 17 - 18

1 	Definitions

  - Architect/Engineer means a person registered as an architect pursuant to Article 249a, Tex. Civ. Stat. Ann., as a landscape architect pursuant to Article 249c, Tex. Civ. Stat. Ann., and/or a person licensed as a professional engineer pursuant to Article 327la, Tex. Civ. Stat. Ann., or a firm employed by Owner to provide professional architectural or engineering services and exercising overall responsibility for the design of a Project or a significant portion thereof, and performing certain contract administration responsibilities as set forth in the Contract.

  - Contractor means the individual, corporation, company, partnership, firm or other organization that has contracted to perform the Work under the Contract with the Owner.

  - Owner means the State of Texas acting through any responsible instrumentality of the State of Texas, which is identified in the Contract as the Owner.

  - Owner’s Designated Representative (ODR) means the individual appointed or assigned by the Owner to be its on-site representative during the Project, to exercise certain power on behalf of the Owner and to undertake certain contract administration activities as specifically outlined in the Contract.

  - Contract means the Contract Documents between the Owner and the Contractor.

  - Contract Date is the date of the Owner-Contractor Agreement is effective between the Owner and Contractor.

  - Contract Time means the period between Date of Commencement and the date scheduled for substantial completion in the Contract Documents, as may be amended by Change Order.

  - Day means a calendar day, unless otherwise specifically stipulated.

  - Contract Documents means the Owner-Contractor Agreement, the Conditions of the Contract the Drawings, the Specifications, the Bidding Documents, Advertisement, Invitation and Instruction to Bidders, Contractor’s Proposal, Contract Award and all Addenda issued prior to and any Change Orders issued after execution of the Contract.

  - Change Order Request (COR) means an Owner-generated document which describes a change in the Work, including a description and Drawings and Specifications, as necessary, to inform the Contractor of the nature of the change.

  - Change Order Proposal Evaluation (CPE) means a Contractor-generated document in response to a Change Order Request (COR) which states the adjustment necessary to Contract Sum and Time, if any, in response to the changed work described in the Change Order Request (COR).

  - Change Order means a written modification of the Contract between the Owner and Contractor, signed by the Owner, the Contractor and, in the case of a Type I change only, the Architect/Engineer.

  - Schedule of Values means the detailed breakdown of the cost of the materials and labor necessary to accomplish the Work as described in the Contract Documents, submitted by Contractor for approval by Owner and Architect/Engineer.

  - Shop Drawings means the drawings, diagrams, illustrations, schedules, performance charts, brochures and other data which are prepared by the Contractor or any Subcontractor, manufacturer, supplier or distributor, and which illustrate some portion of the Work

2.  Compliance with Laws.  In the execution of the Contract Documents and the Work, the Contractor shall comply with all applicable State and Federal laws, including but not limited to, laws governing labor, equal employment opportunity, safety, environmental protection and prevailing wage rates.  The Contractor shall make himself familiar with and at all times shall observe and comply with all Federal, State and Local laws, ordinances and regulations which in any manner affect the conduct of the Work.  The Contractor shall indemnify and save harmless the State and its official representatives against any claim arising from violation of any such law, ordinance or regulation by himself, his subcontractors and his employees.  Except where expressly required otherwise by applicable laws and regulations, neither Owner nor the Architect/Engineer shall be responsible for monitoring Contractor’s compliance with any laws or regulations.

2.1. The Contractor shall cooperate with city or other governmental officials at all times where their jurisdiction applies.  The Contractor shall make application pay all fees and provide supporting documentation necessary to secure permits, which are required for the performance of the Contract Documents and the Work. Contractor has a continuing obligation throughout the term of the Contract to conduct his operations under duly issued permits and, in the event Contractor loses or has revoked a necessary permit, Contractor must take immediate steps to apply for and receive another permit.

3.  State Sales and Use Taxes.  The Owner qualifies for exemption from State and Local Sales and Use Taxes pursuant to the provisions of Chapter 151, Texas Tax Code.  The Contractor may claim exemption from payment of applicable State taxes by complying with such procedures as may be prescribed by the State Comptroller of Public Accounts.

4.   Duty to Pay Prevailing Wage Rates. 	The Contractor shall pay not less than the wage scale of the various classes of labor as shown on the “Prevailing Wage Schedule” provided by the Owner.  The specified wage rates are minimum rates only.  The Owner will not consider any claims for additional compensation made by any Contractor because the Contractor pays wages in excess of the applicable minimum rate contained in the Contract.  The “Prevailing Wage Schedule” is not a representation that quantities of qualified labor adequate to perform the Work may be found locally at the specified wage rates. The full statutory penalty of $60.00 per day of violation per worker shall be retained by the Owner to offset its administrative costs, pursuant to Texas Government Code §2258.023 for any infraction found to have occurred during the construction project.

5. Copies Furnished.  The Contractor will be furnished free of charge the 12 f complete sets of the Contract Drawings and Specifications.  Additional complete sets of Drawings and Specifications, if requested, will be furnished at reproduction cost to the one requesting such additional sets.

6.  Resolution of Conflicts in Documents. In the event of conflict between Drawings and Specifications, the Specifications shall prevail.  In the event of conflict among provisions of Specifications, using the CSI format, what is called for in the division of the predominant discipline will govern inconsistent provisions found elsewhere.

6.1 In the event of conflict among the drawings, the large scale drawings prevail over the small scale drawings.

6.2 In order to facilitate its responsibilities for completion of the Work in accordance with and as reasonably inferable from the Contract Documents, prior to commencing the Work, the Contractor shall examine and compare: the Contract Documents; information furnished by the Owner; relevant field measurements made by the Contractor; and any visible conditions at the Site affecting the Work.

7.  Payment Bonds. The Contractor is required to tender to Owner, prior to commencing the Work, performance and payment bonds, as required by Chapter 2253, Texas Government Code.

7.1 A Payment Bond is required if the Contract Price is in excess of $25,000.  A payment bond is payable to the state, in the full amount of the Contract and solely for the protection and use of payment bond beneficiaries who have a direct contractual relationship with the Contractor or a supplier of required materials or labor.  The form of bond shall be approved by the Attorney General of Texas.

  - Corporate sureties authorized to issue bonds shall be qualified and comply with relevant provisions of the Texas Insurance Code.

7.3 The process of requiring and accepting bonds and making claims there under shall be conducted in compliance with Chapter 2253, Texas Government Code.  If for any reason a statutory payment or performance bond is not honored by the surety, the Contractor shall fully indemnify and hold the Owner harmless of and from any costs, losses, obligations or liabilities it incurs as a result.

7.5 Owner shall furnish certified copies of a payment bond and the related Contract to any qualified person seeking copies who complies with §2253.026, Texas Government Code.

7.6 Claims on Payment Bonds. Claims on payment bonds must be sent directly to the Contractor and his surety in accordance with § 2253.041, Texas Government Code.  All Payment Bond claimants are cautioned that no lien exists on the funds unpaid to the Contractor on such Contract, and that reliance on notices sent to the Owner may result in loss of their rights against the Contractor and/or his surety.  The Owner is not responsible in any manner to a claimant for collection of unpaid bills, and accepts no such responsibility because of any representation by any agent or employee.

7.8 Payment Claims when Payment Bond not required.  When the value of  the Contract between the Owner and the Contractor is less than $25,000.00, claimants and their rights are governed by Texas Property Code, §§ 53.231 – 53.239.  These provisions set out the requirements for filing a valid lien on funds unpaid to the Contractor as of the time of filing the claim, actions necessary to release the lien and satisfaction of such claims

8.  Insurance Requirements.

8.1 The Contractor shall carry insurance in the types and amounts indicated in this Article for the duration of the Contract, which shall include items owned by Owner in the care, custody and control of Contractor prior to, during construction and during the warranty period. Contractor must also complete and file the declaration pages from the insurance policies with Owner whenever a previously identified policy period expires during the term of the Contract, as proof of continuing coverage.  Acceptance of the insurance policy declaration pages by the Owner shall not relieve or decrease the liability of the Contractor.

  - Minimum Insurance Coverage’s: The Contractor shall provide and maintain, until the Work covered in this Contract is completed and accepted by the Owner, the minimum insurance coverage’s in the minimum amounts as described below.  Coverage shall be written on an occurrence basis by companies authorized and admitted to do business in the State of Texas and rated A- or better by A.M. Best Company or otherwise acceptable to Owner.

Type of Coverage	Limits of Liability

a. Worker’s Compensation	Statutory

- Employer's Liability

Bodily Injury by Accident	$500,000 Ea. Accident

Bodily Injury by Disease	$500,000 Ea. Employee

Bodily Injury by Disease	$500,000 Policy Limit

- Commercial General Liability, including coverage for the following:

1)     Premises Operations	Combined Single

2)     Independent Contractors	Limit for Bodily

3)     Products/Completed 		Injury and Property

Operations 			Damage of

4)     Personal Injury			$1,000,000

Per occurrence or

5)     Contractual Liability	its equivalent.

- Explosion, Collapse, Underground

- Broad form property damage, to include fire legal liability

d.	Business Automobile Liability owned/leased, owned, hired

Combined single limit for Non-Bodily Injury and Property Damage of $1,000,000

Per Occurrence or its

Equivalent

e.	Owner's Protective Liability Insurance Policy, naming the State of Texas, its employees, and the Architect/Engineer as insured with the following limits:

Bodily Injury                        		$1,000,000 Each Occurrence	                                       $1,000,000 Aggregate

f.  	Builder's Risk Insurance

An all risk policy, including workmanship acceptable to the Owner, in the amount equal at all times to 100% of the Contract Sum.  The policy shall be issued in the name of the Contractor and shall name his Subcontractors as additional insured.  The Owner shall be named as a loss payee on the policy.  The builders risk policy shall have endorsements as follow:

- This insurance shall be specific as to coverage and not considered as contributing insurance with any permanent insurance maintained on the present premises.  If off site storage is permitted, coverage shall include transit and storage in an amount sufficient to protect property being transported or stored.

- For renovation projects and or work, the Owner waives subrogation for damage by fire to existing building structure(s), if building structure(s) is in care, custody or control of Contractor.

- Builder's Risk Policy shall be endorsed to include coverage for existing building structure(s).

- Flood insurance when specified in Supplementary General Conditions or Special Conditions.

- Umbrella coverage when specified in Supplementary General Conditions or Special Conditions.

  - Policies must include the following clauses, as applicable.

- “This insurance shall not be canceled, limited in scope or coverage, or non-renewed until after thirty (30) days prior written notice, or ten (10) days for non-payment of premium, has been given to the Owner.”

- “It is agreed that the Contractor’s insurance shall be deemed primary with respect to any insurance or self insurance carried by the state agency for liability arising out of operations under the Contract with the Owner.”

- “The Owner, it officials, directors, employees, representatives, and volunteers are added as additional insured as respects operations and activities of, or on behalf of the named insured performed under contract with the Owner.”  This is not applicable to the workers’ compensation policy.

- “The workers’ compensation and employers’ liability policy will provide a waiver of subrogation in favor of the Owner.”

- The workers’ compensation insurance coverage must include the responsibility of the General Contractor to provide coverage for every worker either under the general Contractor's policy or under the policy provided by a Subcontractor.  The general Contractor's policy shall provide that, in the event that a Subcontractor's policy fails to provide worker's compensation coverage of a worker that such insurance coverage is provided by the general Contractor's policy.  Contractor shall obtain certificates of coverage from Subcontractors carrying their own policies, prior to any Subcontractor providing services to the Project.

f.       By signing the Contract or providing or causing to be provided a certificate of coverage, Contractor is representing to Owner that all employees of the Contractor who will provide services on the Project will be covered by workers’ compensation coverage for the duration of the Project, that the coverage will be based on proper reporting of classification codes and payroll amounts, and that all coverage agreements will be filed with the appropriate insurance carrier, or in the case of self-insured, with the Texas Workers' Compensation Commission.  Providing false or misleading information may subject Contractor to administrative penalties, criminal penalties, civil penalties or other civil actions.

g.     If insurance policies are not written for the amounts specified in 8.2, Contractor shall carry Umbrella or Excess Liability Insurance for any differences in amounts specified.  If Excess Liability Insurance is provided, it shall follow the form of primary coverage.

h.      The furnishing of the above listed insurance coverage must be tendered prior to execution of the Contract, and in no event later than ten (10) days from Notice of Award.  Failure to provide the insurance in a timely fashion may result in loss of Contractor’s bid bond.

i.     Owner shall be entitled, upon request and without expense, to receive copies of the policies and all endorsements as they apply to the limits set out in 8.2 above.

9.	 Preconstruction Conference. Prior to the issuance of Notice to Proceed, a conference will be held attended by the Owner, Contractor, Architect/Engineer and Subcontractors, as appropriate, to establish a working understanding among the parties as to the Work, schedules, procedures for handling Shop Drawings and other submittals, processing Applications for Payment, maintaining required records and all other matters of importance to the Project and effective communications on Site.

10.	Indemnification of Owner. Contractor covenants and agrees to FULLY INDEMNIFY and HOLD HARMLESS, the Owner and the elected officials, employees, officers, directors, volunteers, and representatives of the Owner, individually or collectively, from and against any and all costs, claims, liens, damages, losses, expenses, fees, fines, penalties, proceedings, actions, demands, causes of action, liability and suits of any kind and nature, including but not limited to, personal or bodily injury, death and property damage, made upon the Owner directly or indirectly arising out of, resulting from or related to Contractor’s activities under this Contract, including any acts or omissions of Contractor, any agent, officer, director, representative, employee, consultant or Subcontractor of Contractor, and their respective officers, agents, employees, directors and representatives while in the exercise of performance of the rights or duties under this Contract.  The indemnity provided for in this paragraph shall not apply to any liability resulting from the negligence of Owner, officers or employees, separate contractors or assigned contractors, in instances where such negligence causes personal injury, death, or property damage.  IN THE EVENT CONTRACTOR AND OWNER ARE FOUND JOINTLY LIABLE BY A COURT OF COMPETENT JURISDICTION, LIABILITY SHALL BE APPORTIONED COMPARATIVELY IN ACCORDANCE WITH THE LAWS OF THE STATE OF TEXAS, WITHOUT, HOWEVER, WAIVING ANY GOVERNMENTAL IMMUNITY AVAILABLE TO THE STATE UNDER TEXAS LAW AND WITHOUT WAIVING ANY DEFENSES OF THE PARTIES UNDER TEXAS LAW.

10.1 The provisions of this Indemnification are solely for the benefit of the parties hereto and not intended to create or grant any rights, contractual or otherwise, to any other person or entity.

10.2 Contractor shall promptly advise the Owner in writing of any claim or demand against the Owner or Contractor known to Contractor related to or arising out of Contractor’s activities under this Contract.

11. Web Based Database - TFC conducts its design and construction management through a web-based management system.  The A/E and Contractor agree to meet this requirement and will perform all project-related functions utilizing this database.  This includes correspondence, submittals, requests for information, voucher requests and processing, amendments and change orders, etc.

12. Safety - Contractor shall be responsible for initiating, maintaining and supervising all safety precautions and programs in connection with the Work.  It shall be the duty and responsibility of the Contractor and all of its Subcontractors to be familiar and comply with all requirements of Public Law 91-596, 29 U.S.C. §§ 651 et. seq., the Occupational Safety and Health Act of 1970, (OSHA) and all amendments thereto, and to enforce and comply with all of the provisions of the Act.  Contractor shall comply with all applicable laws and regulations of any public body having jurisdiction for safety of persons or property to protect them from damage, injury or loss and shall erect and maintain all necessary safeguards for such safety and protection.

12.1 Contractor shall notify owners of adjacent property and of underground facilities and utility owners when prosecution of the Work may affect them or their facilities, and shall cooperate with them in the protection, removal, relocation and replacement of their facilities and/or utilities.

12.2. In any emergency affecting the safety of persons or property, the Contractor shall act reasonably to prevent threatened damage, injury or loss.  Contractor shall give the ODR and Architect/Engineer prompt notice if Contractor believes that any significant changes in the Work or variations from Contract Documents have been caused by its emergency response or any additional compensation or extension of time claimed by the Contractor.

  - Authorized agents of Contractor shall respond immediately to call out at anytime of day or night when circumstances warrant the presence of Contractor to protect the Work or adjacent property from damage, restriction or limitation or to take such action pertaining to the Work as may be necessary to provide for the safety of the public.  Should Contractor fail to respond, Owner is Owner may deduct any cost of remedial action from the funds due the Contractor under the Contract.

13. Environmental Safety and Control. Upon encountering any previously unknown potentially hazardous waste material, or other materials potentially contaminated by hazardous waste, the Contractor shall immediately stop work in and secure the affected area, and notify the ODR. All subcontracts shall expressly bind subcontractors to the same duty. On receiving such notice, the ODR shall promptly engage qualified experts to make such investigations and conduct such tests as may be reasonably necessary to determine the existence or extent of any environmental hazard. As soon as possible upon completion of this investigation, the ODR shall issue a written report to the Contractor identifying the material or materials found and indicating any necessary  steps to be taken to treat, handle, transport or dispose of the material. The Owner may hire third-party contractors to perform any or all such steps. Should compliance with the ODR’s instructions result in an increase in the Contractor’s cost of performance, or delay the Work, an adjustment in the contract price or time may be claimed by the Contractor through a change order as described on page 21. The Contractor shall fully indemnify, save and hold harmless the Owner of and from any costs, losses, damages or liabilities resulting from its failure, or the failure of its subcontractors, to comply strictly with these provisions.

14	  Routine Testing. If the Contract Documents, laws, ordinances, rules, regulations or orders of any public authority having jurisdiction require any work to be inspected, tested or approved, the Contractor shall give the Owner and the Architect/Engineer timely notice of its readiness and of the date arranged so the Architect/Engineer may observe such inspection, testing or approval.  Should the material or work fail to comply with the requirements of the Contract Documents, the Contractor shall bear all costs of the testing, inspection or approval as well as the cost of replacement of unsatisfactory material. The costs of routine testing shall be borne by the Owner

14.1	Materials incorporated into the Project will be subject to routine tests as required to insure their compliance with the specifications.  Materials to be tested include, but are not limited to, the following:

- Concrete - Primary mix design, slump tests and cylinder compression tests.

- Steel - Tensile tests.

- Welds - Field inspection and X-ray equipment.

- Soils - Subsoil investigation, physical analysis and compaction tests.

- Pavement - Physical analysis and compaction tests.

- Roofing - Samples cut from in-place roof.

Any other basic materials for which standard laboratory test procedures have been established may also be included if doubt as to their quality should arise.  Any testing, as described, will be done at the discretion of the Owner who will bear all costs.  The Contractor shall be held responsible for providing samples of failure, of the failure of its subcontractors, to comply strictly with these

14.2.	Should any of the routine tests indicate that a material does not comply with the job requirements, the burden of proof of compliance shall be with the Contractor, subject to the following conditions?

- Contractor may select the laboratory for further testing, but selection must be approved by the Owner.

- Quality and nature of tests will be determined by the Owner.

- All tests shall be taken in the presence of the Owner or ODR.

- If tests prove that the material complies with specifications, the laboratory fees will be paid by the Owner.  If noncompliance is proved, laboratory fees will be paid by the Contractor.

- Proof of noncompliance will make the Contractor liable for any corrective action which the Owner feels is prudent, including complete removal and replacement of defective material.

14.3.1. All subsequent tests on original or replaced materials conducted as a result of prior failure will be paid by the Contractor

- Contractor’s Submittals.  The Contractor shall submit, with reasonable promptness consistent with the Project Schedule and in orderly sequence, all Shop Drawings, Samples or other information required by the Contract Documents, or subsequently required by the Architect/Engineer as governed by Change Orders.  The Contractor shall review each submittal for compliance with Contract Documents and shall certify that it has done so by stamp, or otherwise, affixed to each copy thereof.  Submittal data presented without such the Contractor certification will be returned without review or other comment, and any delay resulting therefrom will be the Contractor's responsibility.

- Schedule of Values. Within twenty (20) days of Notice to Proceed under the Contract, the Contractor shall submit to the ODR and the Architect/Engineer for approval a Schedule of Values, accurately itemizing material and labor for the various classifications of the Work.  The approved Schedule of Values will be used as the basis for the progress payments under the Contract.

  - Progress Payments. Periodic progress payments will be made to the Contractor for Work performed, and materials in place or suitably stored and protected on sites or as otherwise agreed to by the Owner and the Contractor.  Payment shall not become due until receipt by the ODR or his designee of a correct and complete Pay Application, certified by the Architect Engineer pursuant to this article.

  - Preliminary Pay Worksheet.   Each month, the Contractor shall submit to the Architect Engineer and the ODR a complete, clean copy of a Preliminary Pay Worksheet, which shall attach the following:

The Contractor’s estimate of the amount of Work performed, labor furnished and materials incorporated into the Work, using the approved Schedule of Values; and  may require;

A schedule update, HUB Subcontracting Plan Reports, and such additional documentation as Owner may require.

16.3	Contractor’s Periodic Invoice.  As soon as practicable, but in no event later than seven days after  receipt of the Preliminary Pay Worksheet from the Contractor, the Architect/Engineer and ODR shall meet with the Contractor to review  the Preliminary  Pay Worksheet  and to observe the condition of the Work. On the basis of this review, the ODR and the AE may require modifications to the Preliminary Pay Worksheet prior to the submittal of a Periodic Invoice and within seven (7) days after the periodic review meeting, the Contractor shall submit a revised pay application reflecting all required modifications to the invoice. The A/E shall within five (5) days after receipt of the Contractors Periodic Invoice, review and approve (and/or reject) Contractors periodic invoice based on completeness, and in accordance with the contract documents. The Contractor shall attach all additional documentation required by the ODR and AE, as well as his affidavit swearing or affirming that all payrolls, bills for labor, materials, equipment, subcontracted work or other indebtedness connected with the Contractor’s Periodic Invoice have been paid or will be paid within the time specified in Chapter 2251, Government Code.  Failure to provide all documentation for payment processing, with the periodic invoice, will cause the payment to not be processed and the documents to be returned to the Contractor.

  - Owner’s Duty to Pay  The Owner shall have no duty to pay the Contractor except on receipt by the ODR of (1) a complete Periodic Invoice certified by the AE or (2) receipt by the ODR of a complete Periodic Invoice accompanied by the Contractor’s affidavit certifying the failure of the AE to timely certify a complete Periodic Invoice.

  - Retainage   Retainage shall be withheld in the amount of 10% of the total amount earned to date for projects with a contract amount up to and including $400,000 and in the amount of 5% of the total amount earned to date for projects with a contract amount exceeding $400,000.

  - Retainage so withheld shall be managed in conformance with Subchapter B, Chapter 2252, Texas Government Code.

  - Reduction to Cover Loss	The Owner may reduce any Periodic Invoice prior to payment  to the extent necessary to protect the Owner from loss on account of actions of the Contractor, including, but not limited to:

- Defective work not remedied;

- Damage to work of a separate contractor;

- Failure to maintain scheduled progress;

- Failure to comply with the requirements of Texas Government Code Chapter 2258 (Prevailing Wage Law); or

- For Contracts with a value of less than $25,000 for which no payment  bond is posted, receipt of written notice by the Owner of unpaid bills, filed in conformance with § 53.232, Texas Property Code. Any funds so withheld shall be released to the Contractor if he furnishes a bond for release of lien.

  - Title to all material and Work covered by progress payments transfers to the Owner upon payment. Transfer of title to Owner does not relieve the Contractor of the sole responsibility for the care and protection of materials and work upon which payments have been made, or the restoration of any damaged work, or waive the right of the Owner to require the fulfillment of all the terms of the Contract.

  - Progress payments to the Contractor shall not release the Contractor or his surety from any obligations under this Contract.

17.   	Owner Quality Assurance. The Owner will make periodic visits to the site to familiarize itself with the progress and quality of the Work, conduct inspections and tests and to determine if the Work is proceeding in accordance with the Contract Documents. The Contractor shall provide sufficient, safe and proper facilities at all reasonable times for observation and/or inspection of the Work by the authorized representatives of the Owner.

  - The Contractor shall not cover up any work with finishing materials or other building components prior to an inspection of the work by the Owner.  Should corrections of the work be required for approval, cover up shall be delayed until another inspection can be made and approval is indicated. Provided 48 hours notice for request for cover-up.

18 Substantial Completion Inspection(s) When the Contractor considers the entire Work Substantially Complete, the Contractor shall so notify the ODR and the Architect/Engineer in writing that the Work will be ready for Substantial Completion Inspection on a date certain. The Contractor shall include with this notice a list of items to be completed or corrected prior to final inspection. On the date indicated by Contractor, or as soon thereafter as is practicable, the ODR, the Architect/Engineer, and the Contractor shall inspect the work and if the Architect/Engineer determines that the Work is Substantially Complete a Certificate of Substantial Completion shall be issued to the ODR and Contractor, fixing the date of Substantial Completion. The Architect/Engineer shall submit with this certificate a list of items to be completed prior to final inspection (the Pre-Final Punchlist). This list may include additional items not included on the Contractor's list, which are deemed necessary by the Architect/Engineer or by the Owner to correct or complete prior to Final Inspection.

  - Pre-Final Punch List The Contractor shall complete all outstanding items identified in the substantial completion (pre-final Punchlist).  Upon completion of all items Contractor shall notify A/E and Owner within 48 hours notice to review work associated with a pre-final Punchlist.  All work must be completed according to the contract documents. Final Completion shall be a condition precedent to the Contractor's right to receive Final Payment.

18.3  Requests for Final Payment Within Thirty (30) days following the date of Final Completion certified by the Architect/Engineer, the Contractor shall submit a certified Application for Final Payment, including all sums held as Retainage, to the Architect/Engineer for his review and approval.

  - Final Payment Documentation  The Contractor shall submit, prior to or with the Application for Final Payment, all close out documents, including maintenance and operating instructions, guarantees and warranties, certificates, record documents and all other items required by the Contract Documents. The Contractor shall also submit an affidavit that all payrolls, bills for materials and equipment, subcontracted work and other indebtedness connected with the Work, except as specifically noted, have been paid or will be paid or otherwise satisfied within the period of time required by Chapter 2251, Texas Government Code. If required by the Owner, the Contractor shall furnish documentation establishing payment or satisfaction of all such obligations, such as receipts, releases and waivers of claims arising out of the Contract, to the extent and in such form as may be designated by the Owner. The Owner is entitled to rely upon this affidavit; the Contractor may not submit a claim on behalf of a subcontractor or vendor if that claim has not been noted as an exception in the affidavit.

  - Architect/Engineer Approval:  Within Ten (10) days after submission of final payment by the Contractor, the A/E shall review for completeness the Contractors Final Payment, in accordance with 18.3 above.

18.5. Offsets and Deductions: The Owner may deduct from the Final Payment all sums due from the Contractor for any reason, and as Liquidated Damages.  If the Certificate of Final Completion notes any Work remaining incomplete or defects not remedied, the Owner may deduct the reasonable cost of remedying such deficiencies from the Final Payment. If such deductions are made, the Owner shall identify each deduction made and the reason therefore, and furnish the Contractor with an explanation of the deduction and the amount deducted on or by the 21st day after Owner's receipt of an approved or deemed approved Application for Final Payment.

18.6. Final Payment Due. Final Payment shall become due and payable by Owner, subject to all allowable offsets and deductions, on the 31st day next following the receipt of the approved or deemed approved Application for Final Payment.  If the Contractor disputes any amount deducted by the Owner, the Contractor shall give notice of the dispute on or before the thirtieth day next following receipt of Final Payment; failure to do so will bar any subsequent claim for payment of amounts deducted.

18.7 Effect of Final Payment:  Final Payment shall constitute a waiver of all claims by the Owner relating to the condition of the Work except those arising from (1) faulty or defective Work appearing after Substantial Completion (latent defects); (2) failure of the Work to comply with the requirements of the Contract Documents; (3) terms of any special warranties required by the Contract Documents, and (4) claims arising from personal injury or property damage to third parties. Final payment shall constitute a waiver of all claims by the Contractor except those specifically enumerated at the time of Final Payment. Provided, however, that the Contract shall not be deemed fully performed and closed until the expiration of all periods provided under the Contract Documents for the Contractor to submit a claim or protest a ULCO.

19 Contractor's General Warranty and Guarantee Contractor warrants to the Owner that all Work shall be executed in accordance with the Contract Documents, complete in all parts and in accordance with approved practices and customs, and of the best finish and workmanship.  Unless otherwise specified, all materials and equipment incorporated in the Work under the Contract shall be new. The Owner may, at its option, agree in writing to waive any failure of the Work to conform to the Contract Documents, and to accept a reduction in the Contract Price for the cost of repair or diminution in value of the Work by reason of such defect. Absent such a written agreement, however, the Contractor's obligation to perform and complete the Work in accordance with the Contract Documents shall be absolute and is not waived by any inspection or observation by the Owner, Architect/Engineer or others, by making any progress payment or final payment by the use or occupancy of the Work or any portion thereof by the Owner, at any time, or by any repair or correction of such defect made by the Owner.

19.1 Warranty Period.  Except as otherwise specified, the Contractor shall repair all defects in materials, equipment or workmanship appearing within one year from the  date of Substantial Completion  of the Work as a whole. Upon receipt of written notice from the Owner of the discovery of any defects, the Contractor shall promptly and at its own cost remedy the defects and replace any property damaged therefrom. In case of emergency where delay would cause serious risk of loss or damage to the Owner, or if the Contractor, after notice, fails to proceed promptly and remedy within 30 days or within another period of time which has been agreed to in writing, in compliance with the terms of the warranty and guarantee, the Owner may have the defects corrected and the Contractor and his surety shall be liable for all expenses incurred.

20 Site Visit The Contractor is responsible for having visited the Site and having ascertained pertinent local conditions such as location, accessibility, and general character of the Site or building, the character and extent of existing Work within and adjacent to the Site, and any other Work being performed thereon at the time of the submission of its proposal.  Any failure to do so will not relieve it from responsibility for successfully performing the Work without additional expense to the Owner.

  - Concealed Site Conditions If, in the performance of the Contract, subsurface, latent or concealed conditions at the Site are found to be materially different from the information included in the bid documents, or if unknown conditions of an unusual nature are discovered differing materially from the conditions usually inherent in Work of the character shown and specified, the Owner shall be notified in writing of such conditions before proceeding with the Work. If necessary, the Owner shall develop a solution and provide it to Contractor.  If the solution prompts changes to the Contract Amount and/or Time, the Contract shall be adjusted.

21    Minor Changes: The Architect/Engineer, with concurrence of the Owner, will have authority to order minor changes in the Work not involving an adjustment in the Contract Sum or an extension of the Contract Time.  Such changes shall be effected by written order, which the Contractor shall carry out promptly.

21.1	Administration: All changes in the Contract shall be administered in accordance with procedures approved by the Owner.

21.2	Routine changes All Changes must be done as requested by the A/E and as approved in writing by the Owner.  The Contractor is to provide detailed breakdown of all pricing for each change, with all supportive backup documentation.  Except for emergency conditions defined below, approval of the Contractor's cost proposal by the Architect/Engineer, Using Agency and Owner will be required for authorization to proceed with the Work being changed.  The Owner will not be responsible for the cost of work changed without prior approval and the Contractor may be required to remove work so installed.

21.3	Emergency changes: To save life or property Emergency Changes may be initiated by the Contractor alone with the claimed cost of such work to be fully documented as to necessity and detail of the reported costs.

21.4	Allowable Overhead and Profit Costs: The amounts that the Contractor or his Subcontractors add to a Change Order for profit and overhead will also be considered by the Owner before approval is given.  The amounts established hereinafter are the maximums that are acceptable to the Owner without a full and complete justification acceptable to the Owner.

1. For work performed by his forces, the Contractor will be allowed the actual amount for materials, the total amount of wages paid for labor, and the total cost of Federal Old Age Benefit (Social Security Tax) and of Worker's Compensation and Comprehensive General Liability Insurance, plus Bond cost if the size of the change warrants revision of the Bonds.  To the total of the above costs, the Contractor will be allowed to add a percentage as noted below to cover overhead and profit combined.  Overhead shall be considered to include insurance other than mentioned above, field (superintendent, etc.)  and office supervisors and assistants, use of small tools, incidental job burdens and general Home Office expenses, and no separate allowance will be made therefore.  Allowable percentages for overhead and profit on changes will not exceed 15% on the first $10,000.00, 10% on the next $10,000.00 and 7-1/2% on the balance over $20,000.00, for any specific Change Order.

2.	For subcontracted work the Subcontractor shall figure his costs, overhead and profit as described above for the Contractor's work and to that total cost the Contractor will be allowed to add a maximum of 10% on the first $10,000.00, 7-1/2% on the next $10,000.00 and 5% on the balance over $20,000.00.

3.	For small Change Orders, the allowance to the Contractor for profit and overhead for work done by his own forces or by Subcontractors will be a minimum of $50.00.

4.	On changes involving both additions and deletions, percentages for overhead and profit will be allowed only on the net addition.

5.	The owner does not accept and will not pay for additional contract cost detailed by accounting records under the title of "Extended Overhead" or "Cost Damages caused by Delays".

- The owner reserves the right of ownership of any time identified as "Float Time", where such time is the time between the contractor's scheduled completion and the date of completion as stipulated in the contract award.  The owner reserves the right of ownership of this time, without sacrificing the choice to determine that the work of the contract has been completed prior to the stipulated contract time in the awarded contract, thereby allowing work completion which may result in the possible use and benefit by the owner prior to the scheduled completion date.

22.  Contract Time.  The Contract Time will be measured from the date designated in the Notice to proceed to the date specified for completion by the Contract Documents, including any modification by Change Order.  Failure to achieve Substantial Completion within the Contract Time will subject the Contractor to Liquidated Damages. Unless otherwise specified in the Special Conditions or elsewhere in the Contract Documents, the date of Contract Completion shall be the date on which the Work is certified as Substantially Complete.

22.1	Work Progress Schedule. The Contractor shall submit in duplicate to the Owner and the Architect/Engineer, for review and acceptance, a proposed Progress Schedule for the Work.  The Progress Schedule shall show a schedule in a logical sequence that shows all work activities in detail as approved by the A/E and the Owner.  If required by the Special Conditions, the Contractor shall also submit a separate Submittal Schedule, correlated with the Progress Schedule that shows the dates the Contractor intends to make the required submittals.

22.2	Schedule Requirements.  The Progress Schedule should be accurate and reliable representations of the progress of the Work to date, and of the Contractor’s actual plans for its completion.  The Progress Schedules shall be capable of measuring and forecasting the effect of delaying events on completed and uncompleted activities.  Submittal of a schedule, schedule revision or schedule update constitutes the Contractor’s representation to the Owner and Architect/Engineer that the Contractor will follow the schedule as submitted in performing all Work as yet not completed, and that all progress to date shown on the schedule is accurately depicted.

22.3	Schedule Updates.  The Progress Schedule and Submittal Schedule (if required) shall be updated periodically to reflect progress to date, and current plans for completing the Work.  The form and contents of the updates, and the required update interval, shall be as specified the Special Conditions.  The updated Progress Schedule shall be submitted to the Owner, and the Architect/Engineer for acceptance, and the Owner shall have no duty to make progress payments until the updated Progress Schedule has been timely submitted.  The Contractor shall show the anticipated date of completion reflecting all extensions of time granted as of the date of the update.   The Contractor may revise the Progress Schedule at any time when in the Contractor’s judgment it becomes necessary for the management of the Work.  The Contractor shall submit any schedule revision to Owner and AE for acceptance before it is implemented.

22.4	Effect of Schedule Submittal.  Submittal of the Progress Schedule, and successive updates or revisions, is for the information of the Owner and Architect/Engineer, and to permit the coordination of their activities with those of the Contractor. Owner and AE shall accept or reject the submittal of a schedule within the same period allowed for review of other submittals. Acceptance of a schedule, schedule update or revision constitutes the Owner’s agreement to coordinate their own activities with the Contractor’s activities as shown on the schedule.  Acceptance of a Progress Schedule, update or revision does not indicate the approval of the Contractor’s proposed sequences and duration.  Acceptance of a Progress Schedule update or revision indicating late completion does not constitute the Owner’s consent to a late finish, or waive either the Contractor’s responsibility for timely completion or the Owner’s right to damages for the Contractor’s failure to do so.

22.5 Ownership of Float.  Float time contained in the Progress Schedule is not for the exclusive benefit of the Contractor or the Owner, but may be consumed by either as needed.

23 	Time Extension Requests. If the Contractor believes that the completion of the Work has been delayed by a circumstance designated as excusable, other than inclement weather, he shall give the Owner written notice, stating the nature of the delay and the activities potentially affected, within 30 calendar days after the onset of the event or circumstance giving rise to the excusable delay.  Such claims should be accompanied by sufficient written evidence to document the delay. In the case of a continuing cause of delay, only one claim is necessary.   Claims for extensions of time shall be stated in numbers of whole or half calendar days Claims for the cost of Excusable Compensable Delays shall be submitted in writing within 90 calendar days after the cessation of the cause of the delay.  The Contractor and Owner recognize and agree that it is beneficial to each to identify delays and make necessary schedule adjustments promptly, and that a Progress Schedule prepared and updated by the Contractor provides an effective tool for measuring and tracking the impact of delays.  Therefore, it is agreed that no extension of time will be granted unless the required notice is submitted timely, and with sufficient documentation.

23.1 Contents of Time Extension Requests.  Each Time Extension Request shall be accompanied by a quantitative demonstration of the impact of the delay on project completion time, based on the current Progress Schedule.  No time extensions shall be granted for delays that do not affect the Project completion time.

23.2 Owner’s Response. The Owner shall respond to the Time Extension Request by providing to the Contractor written notice of the number of days granted, and giving its reason if this number differs from the number of days requested by the Contractor.  Such an Extension of Time is effective on the date the Owner’s notice is received by the Contractor, but a Change Order reflecting the Extension of Time shall be executed by the parties.   The Owner will respond to each properly submitted Time Extension Request within 15 calendar days following its submittal; if the Owner cannot reasonably make a determination about the Contractor’s entitlement to a time extension within that time, the Owner shall so notify the Contractor in writing. Upon written agreement with the Contractor, the Owner shall then have not more than 30 additional calendar days to prepare a final response.

24   Failure to Complete Work within the Contract Time. Time is of the essence of this Contract. The Contractor’s failure to complete the Work within the Contract Time will cause damage to the Owner. These damages shall be liquidated by agreement of the Contractor and the Owner, as set forth in the Special Conditions.

24.1 Collection of Liquidated Damages.  The Owner may collect Liquidated Damages due from the Contractor directly or indirectly by reducing the contract sum in the amount of Liquidated Damages stated in the Special Conditions and the Contract

25 Terminations by Owner for Cause The Owner may, without prejudice to any right or remedy terminate the employment of the Contractor and take possession of the site and of all materials, equipment, tools, construction equipment and machinery thereon owned by the Contractor, under the following circumstances:

- Persistent or repeated failure or refusal, except during complete or partial suspensions of work authorized under the Contract Documents, to supply enough properly skilled workmen or proper materials;

- Persistent disregard of laws, ordinances, rules, regulations or orders of any public authority having jurisdiction;

- Persistent failure to prosecute the work in accordance with the Contract Documents, and to insure its completion within the time, or any extension thereof, specified in this contract;

- Failure to remedy defective work condemned by the ODR;

- Failure to pay subcontractors, laborers, material men and suppliers pursuant to Texas Government Code Chapter 2251;

- Persistent endangerment, by the Contractor or its Subcontractors or other vendors, of the safety of labor or of the Work itself;

- Failure to supply or maintain statutory bonds, or the supply or maintain Required insurance; or

- Any other material breach of the Contract.

The Owner reserves the right to terminate at any time for any of the above listed causes.  Failure to exercise the right to terminate in any instance or for any proper reason shall not be construed as waiver of the right to do so in any other instance or for any other proper reason.

The ODR shall give the Contractor and its Surety thirty days’ prior written notice of its intent to terminate for any of the above reasons. If the Contractor or the Surety demonstrates, to the satisfaction of the Owner, that the condition or conditions upon which the notice of termination is based have been removed, corrected, or will not recur, then the Owner shall rescind the notice and the Contract shall continue unmodified, and the Contractor shall not be entitled an extension of time.

25.1  Completion of Work after Termination: Should the Contractor or the surety fail to so demonstrate within thirty days following receipt of such notice, or fail to satisfy the Owner that the condition or conditions upon which the notice of termination is based have been removed, corrected, or will not recur, the Owner may arrange for completion of the Work and deduct the cost thereof from the unpaid Contract sum remaining, including the cost of additional Architect/Engineer services made necessary by such default or neglect, in which event no further payment shall then be made by the Owner until all costs of completing the Work shall have been paid.  If the unpaid balance of the Contract Sum exceeds the costs of finishing the Work, including compensation for the Architect/Engineer's additional services made necessary thereby, such excess shall be paid to the Contractor.  If such costs exceed the unpaid balance, the Contractor or his surety shall pay the difference to the Owner.  This obligation for payment shall survive the termination of the Contract.  The Owner reserves the right, where the Contract is terminated for cause, to take assignment of any and all contracts between the Contractor and its Subcontractors, vendors and suppliers, and the ODR shall promptly notify the Contractor of the contracts the Owner elects to assume. Upon receipt of such notice, the Contractor shall promptly take all steps necessary to effect such assignment.

25.2	Termination for Convenience of Owner. The Owner reserves the right, without breach, to terminate the Contract prior to, or during the performance of the Work, for unforeseen causes not limited to court orders, loss of funding, acts of the federal government to discontinue the work, etc., that may occur and render the Owner’s continued performance of the Contract impossible or illegal. Upon such an occurrence, the following procedures will be adhered to:

- The Owner will immediately notify the Architect/Engineer and the Contractor in writing, specifying the reason for and the effective date of contract termination. Such notice shall also contain any instructions necessary for the protection, storage or decommissioning of incomplete work or systems, and for safety.

- After receipt of the notice of termination, the Contractor shall immediately proceed with the following obligations, regardless of any delay in determining or adjusting any amounts due at that point in the Contract.

1. 	Stop all work.

2.   Place no further subcontracts or orders for materials or services.

3.	Terminate all subcontracts.

4.	Cancel all materials and equipment orders as applicable.

5.	Take action that is necessary to protect and preserve all property related to this    Contract which is in the possession of the Contractor.

- When the Contract is terminated for the Owner’s convenience, the Contractor may recover from the Owner payment for all Work executed, including any additional work required pursuant to the notice of termination, and for any provable loss and reasonable expenses attributable to the Work resulting from such termination.

25.3	Termination by Contractor.  If the Work is stopped for a period of ninety (60) days under an order of any court or other public authority having jurisdiction, or as a result of an act of government, such as a declaration of a national emergency making materials unavailable, through no act or fault of the Contractor or a Subcontractor or their agents or employees or any other persons performing any of the Work under a contract with the Contractor, then the Contractor may, upon thirty (30) additional days’ written notice to the ODR, terminate the Contract and recover from the Owner payment for all Work executed and for any provable loss and reasonable expenses attributable to the Work resulting from such termination. If the cause of the work stoppage is removed prior to the end of the thirty (30) day notice period, the Contractor may not terminate the Contract.

  - Settlement on Termination. When the Contract is terminated for any reason, the Contractor shall, at any time prior to 180 days of the effective date of termination, submit a final termination settlement proposal to the Owner based upon recoverable costs.  If the Contractor fails to submit the proposal within the time allowed, the Owner may determine the amount due to the Contractor because of the termination and shall pay the determined amount to the Contractor.

- Dispute Resolution; The dispute resolution process provided for in Chapter 2260 of the Texas Government Code shall be used, as further described herein, by the Owner and the Contractor to attempt to resolve any claim for breach of contract made by the Contractor:

  - The submission, processing and resolution of the Contractor’s claim is governed by the published rules adopted by the attorney general pursuant to Chapter 2260, as currently effective, hereafter enacted or subsequently amended.

  - Neither the occurrence of an event nor the pendency of a claim constitutes grounds for the suspension of performance by the Contractor, in whole or in part.

- Severability.  If any provision, sentence, clause or article of this Contract is found to be invalid or unenforceable for any reason, the remaining provisions shall continue in effect as is the invalid or unenforceable provision were not in the Contract.  All provisions, sentences, clauses and articles of this Contract are severable for this purpose.

28 	Parties Bound.  Execution of this Contract by each party binds the entity represented as well as its employees, agents, successors and assigns to its faithful performance.

29   No waiver of Sovereign Immunity.  Nothing herein shall be construed as a waiver of the state’s sovereign immunity.

- Written Notice.  Written notice shall be considered to have been duly given if the document is delivered in person to the individual or member of the firm or to an officer of the corporation for whom it is intended, if delivered at or sent by registered or certified mail to the last business address known to one who gives the notice, or transmitted by fax machine, with a receipt retained to prove delivery.  Notice is deemed effective when given rather than when received.