## Steps
Method of Procedures and Performance (MOPP)
Steps | Date | Day | Start Time | Finish Time | Procedure
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## JOB AIDE
Method of Procedures and Performance (MOPP)
Steps | Date | Day | Start Time | Finish Time | Procedure
1 | 2025-08-01 | Friday | 8:00 | 13:00 | Materials will arrive onsite. Staging will be on the north side of the parking lot.
2 | 2025-08-04 | Monday | 8:00 | 17:00 | Crews will set up equipment on the north side of the parking lot.
3 | 2025-08-04 | Monday | 10:00 | 17:00 | Electrician to remove panels and evaluate problems
4 | 2025-08-05 | Tuesday | 8:00 | 17:00 | Clean up and move out.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Example
Complete this table with as much detail as possible for TFC review and approval.
Be sure to include notes on when and where TFC support is required.